QIBA fMRI Technical Committee Agenda & Call Summary

Wednesday, March 12th, 2014 at 11 AM CT

DRAFT Call Summary

| In attendance |  |
| --- | --- |
| Ted DeYoe, PhD (Co-Chair) | Zhiyue Jerry Wang, PhD |
| Jeffrey Petrella, MD (Co-Chair) | Yuxiang Zhou, PhD |
| Feroze Mohamed, PhD |  |
| James Reuss, PhD | RSNA |
| David Soltysik, PhD | Joe Koudelik |
| Daniel Sullivan, MD | Madeleine McCoy |

General Announcements:

Bottom of Form

- 2014 QIBA Annual Meeting, May 21-22, 2014 at the Hyatt Regency Crystal City in Arlington, VA – we will not have a face to face breakout session of the fMRI TC.

  - Volunteer willing to present our status report on behalf of co-chairs?

- Reminder - RSNA Call for Abstracts Online Submission site closes at 12 Noon Central (Chicago) Time on April 9, 2014.  http://abstract.rsna.org/ - All QIBA Technical Committees are encouraged to submit RSNA abstracts (i.e., posters, presentations, etc.) based on funded and non-funded project results and overall committee efforts to-date

- Welcome to Dr. Edson Amaro -   Faculdade de Medicina – USP in Sao Paolo Brazil

Reference: Multisite fMRI reproducibility of a motor task using identical MR systems.  Costafreda SG, Brammer MJ, Vêncio RZ, Mourão ML, Portela LA, de Castro CC, Giampietro VP, Amaro E Jr. J Magn Reson Imaging. 2007 Oct;26(4):1122-6.

- !!!Time to Plan Round 4 Projects - so that we are better positioned to start on time in October.   first draft concepts of proposals are needed by April 7, 2014, so that we can meet the schedule outlined below.

QIBA Round 4 (2014-15) Project Proposal Timeline

| Feb – March 2014 | TCs discuss Profile gaps and projects needed to address them |
| --- | --- |
| COB, April 7, 2014 | Concepts due to RSNA. RSNA staff collates and sends to SC by April 11, for discussion on Apr 17, 2014 SC t-con |
| April 17, 2014 | SC discusses concepts for Go/No Go decision TCs are advised as to which concepts should be developed further |
| COB, May 12, 2014 | Revised concepts submitted to RSNA. RSNA collates and sends to SC by May14, for discussion at May 20, 2014 f-2-f SC Meeting |
| May 20, 2014 | SC votes on initial prioritizations. Questions, need for clarifications provided to TCs |
| COB, July 7, 2014 | Final project proposals submitted to RSNA. RSNA staff collates and sends to SC by July 11, for discussion and final decisions on July 17, 2014 SC t-con |
| July 17, 2014 | SC makes final project selections/funding decisions Notifications sent to Project PIs |
| Sept 2, 2014/as soon as Yr2 funding approved by NHLBI | Submit Subcontracts to NHLBI for COA |

4. QIBA/NIBIB Round-3 Funded Project Updates --

- IRB updates

- DRO format questionnaire version 5

- DRO project descriptor file

- DRO template development – status – Dummy DRO sent to Duke

- QIDW – next steps

Discussion

2014 QIBA Annual Meeting

- The fMRI breakout session has been removed from the QIBA meeting agenda

- Dr. Zhiyue Jerry Wang will be in attendance at the meeting and has been asked to consider giving the TC status report on Day 2.

RSNA Call for Abstracts Online Submission

- The committee was reminded of the April 9th submission deadline

Dr. Edson Amaro’s paper was circulated

- Multisite fMRI Reproducibility of a Motor Task Using Identical MR Systems which provides some additional data on reproducibility of BOLD fMRI amplitude and volume at 1.5T.

Round 4 Projects

- First draft concepts of project proposals are due by April 7, 2014.

- Drs. DeYoe and Petrella discussed expanding the DRO Project with a primary focus on intra-subject variability and mitigation strategies

  - Obtaining real outcome data from a significant number of sites

  - Reproducibility

- Dr. Mohamed suggested NIH VideoCast as a resource to view past fMRI Presentations

- Dr. DeYoe requested that ctte members think about project ideas for the next call

  - The goal will be to prioritize chosen topics for development into proposals

Action Items

- A small fMRI f2f meeting was suggested, possibly at the ASNR this year; Dr. DeYoe to follow-up with Dr Elsinger regarding  possible times

- Dr Reuss to contact Dr. Voyvodic with details of next week's DICOM Working Group meeting.

Next calls:

- QIBA fMRI Bias WG call - Tuesday, March 18th, at 10am CT

- QIBA fMRI tech committee call - Wednesday, March 26th, at 11am CT