Timeline for QIBA VolCT 1A Reader Study

1/1-1/15/2009, Completed

- Define basic study protocol

1/1-/30/2009, Completed, Pilot data sent this week to Bob Ford

- Identify Pilot study cases (9 nodules)

- Identify Reader study cases (40 nodules)

1/20/2009-2/6/2009	Petrick now working on draft, will need input from others

- Develop written protocol for reader study

- Develop written analysis plan for data

2/16-2/20/2009

- Conduct Pilot study at RadPharm

2/23-2/27/2009	1A subgroup

- Make any necessary adjustments to reader study protocol

3/1-3/30/2009		RadPharm

- Conduct reader study at RadPharm (3 weeks between reading sessions)

4/1/4/15/2009

- Conduct analysis

- Write RSNA abstract

- Consider future projects/peer-reviewed publication